## Sheet1
MATTERS ARISING
MTG DATE | ITEM | DESCRIPTION |  | RESULT | ACTION
131125 | 12i a | Play Area Report. a) Repairs- ROSPA report. SL indicated he had emailed the ROSPA report [MS given explanation of process] and explained the risk Matrix. He emphasized the issue of liability regarding the report. IW gave his concerns about some of the reporting. He pointed out that some issues could not be resolved due to age and other points were clearly health and safety issues. It was agreed to visit the site and access what need to be done to remedy some of the items. | MS/IW | Meeting took place 070726 with councillors and workforce. Contract agreed with a plan to carry out work prior to next inspection. Initially weekly visits and then reverting to every two months. | COMPLETED
131125 | 12iii | Bus Shelter/noticeboard and village sign IW gave an overview of costs and materials and was directed to carry out the relevant repairs as soon as possible on the bus shelter. | IW | ** RESULT: IW stated he had assessed the work and would obtain materials [Money previously agreed] and the work would completed shortly. | TO BE COMPLETED
191226 | ii | ALLOTMENTS: There was discussion regarding the water project proposed to make the area self-sufficient. SL stated the request heard earlier and agreed in Principle by EB should cover the costs. SL proposed the workers contracted for the Play area would be suitable candidates for construction. SL indicated he planned to request £1200. BH then asked about Hedgerow, and it was agreed that a suitable use of the plants would be skirt the allotments and provide natural cover in the light of the recent damage caused by a vehicle crossing the area. | CLERK | Meeting took place 070726 with councillors and workforce. Contract agreed with a plan to carry out work building water gatherer. Access required from adjacent field after crop harvested. | COMPLETED
120326 | 11iii | Victory Hall – SL stated communities were being encouraged to choose sustainable transport with new grant scheme and East Suffolk Council is inviting organisations to apply for funding towards cycle parking in their local community. The Community Cycle Parking Fund is offering grants of up to £1,000 for the purchase and installation of new or upgraded cycle parking facilities. SL stated he would make an application. | CLERK | SL - Clerk submitted application for grant. | COMPLETED
90526 | 16a | Allotment Matters – SL was requested to acquire signs indicating access limitations to the Council allotments. These were to be green with white lettering. | CLERK | Clerk obtained signs HASKETON COMMUNITY ALLOTMENTS [DOGS ON LEAD PLEASE] CLERK NAME AND CONTACT - TO BE FITTED | COMPLETED
90526 | 16d | d) Play Area - IW would place new posts to support roadside fencing. | IW | PRIORITY AS FENCE HAS FALLEN | OUTSTANDING
20726 | 13iv | Tree Management – SL gave details of an email received regarding a possible tree and plaque from the family of a deceased resident. It was agreed to a blossom tree, but the plaque need to be provided by the family and initial upkeep by them. Clerk to respond. | CLERK | Family conatcted and being progressed. They are willing to pay for tree and maitain it. They will also obtaing a plaque. Site to be established. | COMPLETED
20726 | 13vii | Benches – IW aware one new bench still to be installed on the corner and removed from the Play area. | IW |  | OUTSTANDING